## Sheet1
No. | 2020 Annual Action Plan of Bosome Freho District Assembly
Adopted MDAs Goal(s): BUILD AN INDUSTRALIASED, INCLUSIVE AND RESILIENT ECONOMY
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG | IGF | Donor | Lead | Collaborating
Economic Development
1 | Trade | Construction /Pavement of a lorry park | Asiwa | New | lorry park constructed |  |  |  |  | 550000 |  |  | Wks Dpt, DPO | DA
2 |  | support to SMEs through the Business Advisory Centre (BAC) | Districtwide | on-going | Soaps and Beads produced |  |  |  |  | 15000 |  |  | BAC | DA
3 |  | Construction of Market facilities (stores, Banking hall) with ancillary facilities | Asiwa | On-going | [5 empty] | 650000 |  |  | Wks Dpt, DPO | DA
4 | Industrial Development | Produce cocoa seeds and seedlings for farmers | District wide | on-going | Cocoa, Oil palm, Rice Maize, Tomatoes, seedlings produced |  |  |  |  | 40000 |  |  | AGRIC. DEPT. | DA
5 | Tourism | Established and maintain tourism activities in 6 communities | 1.Ankaase 2.Amormorso | New | Tourism site developed |  |  |  |  | 30000 | 2000 | 80000 | Tourism Authority | DA
6 | Agriculture Development | Ensuring Food Security | Districtwide | On-going | Governmnet initiatives supported |  |  |  |  | 15000 |  |  | AGRIC. DEPT. | DA
7 |  | Construction of office block for Agric Directorate | Asiwa | On-going | Agric. Block completed |  |  |  |  | 200000 |  |  | AGRIC. DEPT. | DA
8 |  | Undertake Rice demonstration / Cultivation Activities | Districtwide | Not commenced | Rice cultivation activities completed |  |  |  |  | 20000 |  |  | AGRIC. DEPT. | DA
9 |  | Support Planting for Food and Jobs through the supply for seeds | Districtwide | on-going | Items for programme distributed |  |  |  |  | 20000 |  |  | AGRIC. DEPT. | DA
10 |  | Support 40 women ruminant and poultry Farmers with Skills on effective construction of improved housing | Districtwide | on-going | Ruminant and poultry farmers supported |  |  |  |  | 5623.27 |  |  | AGRIC. DEPT. | DA
11 |  | Organise field tour to establish farms and reseach institute for 40 women farmers | Anyanso and other communities | New | Field tour to established farms organised |  |  |  |  | 5000 |  |  | Agric. Dpt | DA
12 |  | Installation of baking machine for 20 women | Asiwa | On-going | Baking machines installed |  |  |  |  | 5000 |  |  | Agric and BAC | DA
SUB-TOTAL
Adopted MDAs Goal(s): CREATE AN EQUITABLE, HEALTHY AND DISCIPLINE SOCIETY
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG | IGF | Donor | Lead | Collaborating
Social Services Delivery
13 | Health Delivery | District Response Initiative (DRI) on HIV/AIDS and Prevention of Malaria & MSHARP | Districtwide | on-going | HIV/AID's and Malaria prevention activity done |  |  |  |  | 33481.96 |  |  | DPO/WORKS/HEALTH DEPT. | DA
14 |  | Construction of health Facility | Dannso | New | Health facility constructed |  |  |  |  | 120000 |  |  | DPO/WORKS/HEALTH DEPT. | DA
15 |  | Drilling and mechanisation of 2 No. boreholes at Tebeso II and Nsuta markets to combat COVID-19 pandemic | Tebeso II and Nsuta markets centres | New | Boreholes drilled and mechanised |  |  |  |  | 87905.62 |  |  | WORKS/HEALTH DEPT. | DA
16 |  | Support CHPS compound with basic equipment | District wide | New | Hospital equipment procured |  |  |  |  | 30000 |  |  | DPO/WORKS/HEALTH DEPT.
17 |  | Completion of 1No. CHPS Compound | Freboye | on-going | CHPs completed |  |  |  |  | 18395.3 |  |  | DPO/WORKS/HEALTH DEPT. | DA
18 |  | Renovation / Rehabilitation of COVID-19 Isolation centre | Asiwa | New | COVID-19 Isolation centre completed |  |  |  |  | 50000 |  |  | Wks dept. | DA
19 |  | Drilling of 1No. Borehole for Freboye CHP Compound | Freboye | on-going | CHPs completed |  |  |  |  | 12000 |  |  | DPO/WORKS/HEALTH DEPT. | DA
20 |  | Construction of CHPS Compound | Duase | New | CHPs completed |  |  |  |  | 109948.68 |  |  | HEALTH DEPT. | DA
21 | Education | Fencing of Bosome Freho Sec. Tech. Sch | Asiwa | Standstill | Fencing of SHS completed |  |  |  |  | 43885 |  |  | DPO/WORKS/EDUC. | DA
22 |  | Completion of 1No. 3-Unit Classroom Blk | Minnti | New | 3-Unit Classroom block completed |  |  |  |  | 127352 |  |  | DPO/WORKS/EDUC. | DA
23 |  | Constraction of 1No. 6-Unit classroom Blk | Amantubuom | on-going | 3-Unit Classroom block completed |  |  |  |  | 150000 |  |  | DPO/WORKS/EDUC. | DA
24 |  | Construction of 1No. 6-unit classroom Blk | Nsueam II | on-going | 3-Unit Classroom block completed |  |  |  |  | 200000 |  |  | DPO/WORKS/EDUC. | DA
25 |  | Construction of 1No. 6-unit classroom Blk | Tebeso II | on-going | 3-Unit Classroom block completed |  |  |  |  | 150000 |  |  | DPO/WORKS/EDUC. | DA
26 |  | Constuction of 1No. 6-unit Classroom Blk | Bobiam | New | 3-Unit Classroom block completed |  |  |  |  | 150000 |  |  | DPO/WORKS/EDUC. | DA
27 | Social Welfare and Community Development | Undertake Community care; Register and Monitor PWD activities | Districtwide | on-going | Communal labour supported |  |  |  |  | 5000 |  |  | COMM. DVPT.
28 |  | Construction of community centre | Yapesa | New | Yapesa community centre constructed |  |  |  |  | 100000 |  |  | Social Welfare and Community Devt. | DA
29 |  | Undertake Child Right Promotion and Protection activities | Districtwide | on-going | Women and Children supported |  |  |  |  | 5000 |  |  | Social Welfare and Community Devt. | DA
30 |  | Undertake Justice Administration & Mass Education activities | Districtwide | on-going | Women and Children supported |  |  |  |  | 3635.41 |  |  | Social Welfare and Community Devt. | DA
| SUB-TOTAL | [12 empty] | DA
Adopted MDAs Goal(s): SAFEGUARD THE NATURAL NEVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG | IGF | Donor | Lead | Collaborating
Infrastructure Delivery & Management
31 | Infrastructure Development | Preparation of sector layout/ planning scheme | Asiwa | on-going | Sector layout or planning scheme prepared |  |  |  |  | 40000 |  |  | DPO/WORKS
32 |  | Undertake Maintenance on Quasi-Government Properties(Court Building, Streetlights, Police Station, Market etc) | District wide | on-going | Governmnent properties maintained |  |  |  |  | 15000 |  |  | DPO/WORKS | DA
33 |  | Drilling of 10 No. Boreholes | Selected communities | on-going | Boreholes drilled |  |  |  |  | 116795.5 |  |  | DPO/WORKS | DA
34 |  | Rural Electrification/ procure Streetlights | district wide | on-going | Street lights /Rural electrification maintained |  |  |  |  | 50000 |  |  | DPO/WORKS | DA
35 |  | Reshape of 30KM of Roads | District wide | on-going | Roads reshaped |  |  |  |  | 200000 |  |  | DPO/WORKS | DA
36 |  | Renovation of Assembly Bungalows and office block | Asiwa | Not commenced | Office Bungalows and office block renovated |  |  |  |  | 50000 |  |  | DPO/WORKS | DA
37 |  | Construction of 1No. Semi-detached bungalow | Asiwa | on-going | Semi-detached bungalow constructed |  |  |  |  | 100000 |  |  | DPO/WORKS | DA
38 |  | Support Self-Help Project activities | District wide | on-going | Communities supported with materials |  |  |  |  | 250000 |  |  | DPO/WORKS | DA
39 | Natural ResourceConservation | Sanitation legislation and Enforcement Management (Stray animals) | District wide | New | Septic tank disloge |  |  |  |  | 15000 |  |  | Envital Health | DA
40 |  | Undertake ativities and programmes on solid /liquid waste management ( fumigation activity) | Districtwide | New | Fumigation done |  |  |  |  | 20000 |  |  | Envital Health | DA
41 |  | Planting of trees in disaster prone and mining areas | District wide | New | Disaster prone areas mapped |  |  |  |  | 30000 |  |  | NADMO and Forestry | DA
42 |  | Undertake tree plannting activity in an open areas | Districtwide | New | Trees planted in open areas |  |  |  |  | 40000 |  |  | Forestry commission | DA
43 |  | Re-afforestation of depleted forest reserves | Districtwide | New | Trees planted in depleted forest areas |  |  |  |  | 50000 |  |  | Forestry commission | DA
44 |  | Undertake activities on food hygiene and safty (Undertake food vendor screening activity) | Asiwa | New | Food vendors screened |  |  |  |  | 50000 |  |  | Envital Health | DA
45 |  | Undertake Undertake Education Campaigns on Disaster & Distribution of Relief Items activities | District wide | New | Education campaign and relief items done |  |  |  |  | 30000 |  |  | NADMO | DA
| SUB-TOTAL | [12 empty] | DA
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG | IGF | Donor | Lead
| Adopted MDAs Goal(s): BUILD EFFECTIVE, EFFICIENT AND DYNAMIC INSTITUTIONS | [12 empty] | Collaborating
Management and Administration
46 | Finance and Revenue Mobilisation | Undrtake Public Sensitization on Pay your Levy Campaign | District Wide | on-going | Assembly's properties revaluated |  |  |  |  | 10000 |  |  | WORKS DPT.
47 | Human Resource Management | Undertake staff development / man power skills development activities | Asiwa | New | Human resources activities supported |  |  |  |  | 50000 |  |  | HR | DA
48 | Planning, Budgeting and Coordination | Undertake Monitoring and Evaluation of Assembly's Projects by DPCU | District Wide | on-going | Projects and programmes monitored |  |  |  |  | 40000 |  |  | DPO | DA
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG | IGF | Donor | Lead | Collaborating
Adopted MDAs Goal(s):STRENGTHEN GHANA’S ROLE IN INTERNATIONAL AFFAIRS
Management and Administration
49 | General Administration, Legislative Oversight | Undertake Maintenance activities on Office machines/ euipment | Asiwa | on-going | Office machines maintained |  |  |  |  | 20000 |  |  | ADMIN.
50 |  | Strengthening of Sub-District structures (Support of Area council offices) | Area council centres | on-going | Area councils strengthened |  |  |  |  | 73927.83 |  |  | Plann | DA
51 |  | Renovation / Rehabilitation of Fire and Ambulance Stations | Asiwa | New | Fire and Ambulance station renovated |  |  |  |  | 100000 |  |  | Wks Dpt. | DA
52 |  | Undertake road safety sensitization programme for drivers | Asiwa | New | Drivers Sensitized |  |  |  |  | 20000 |  |  | Police | DA
53 |  | Undertake road safety sensitization programme for motor drivers | Asiwa | New | Drivers Sensitized |  |  |  |  | 30000 |  |  | Police | DA
54 |  | Support to security agencies | District Wide | on-going | Security agencies supported |  |  |  |  | 20000 |  |  | DPO/COMM. DEVPT. | DA
55 |  | Undertake public / town hall meetings | Asiwa | New | Town Hall/ Public Forum organised |  |  |  |  | 30000 |  |  | DPO/BUDGET | DA
| SUB TOTAL | [12 empty] | DA
GRAND TOTAL