## Sheet1
PROPOSED ANNUAL ACTION PLAN FOR BOSOME FREHO DISTRICT ASSEMBLY - 2021
Adopted MDAs Goal(s): BUILD AN INDUSTRALIASED, INCLUSIVE AND RESILIENT ECONOMY
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
Item No. | [5 empty] | 1st | 2nd | 3rd | 4th | DACF/GoG | DDF | IGF/Donor | Lead | Collaborating
Economic Development
1 | Trade | Completion of pavement of a lorry park | Asiwa | Completed | lorry park constructed | [5 empty] | 60000 |  | Wks Dpt, DPO | DA
2 |  | Support to Business Advisory Centre (BAC) Formation of FBO ,Business Counseling, Business orientation, Strengthening Of Association | Districtwide | New | Palm Oil, Dresses, Soaps, Gari, Beads produced |  |  |  |  | 45000 |  |  | BAC | DA
3 |  | Sectional completion of Block "B" with 20-No. market stores and toilet facilities | Asiwa | New | Block "B" of market stores completed | [5 empty] | 505000 |  | Wks Dpt, DPO | DA
4 |  | Completion of Block "B" of market Stores with Banking hall and other ancillary facilities | Asiwa | On-going | Market Stores constructed | [5 empty] | 3000000 |  | Wks Dpt, DPO | DA
5 | Industrial Development | Support for Government Flagship Programmes (1D,1F), (PERD), (PFJ) | District wide | New | Government Flagship Programmes Supported |  |  |  |  | 100000 |  |  | Central Adm. | Agric and BAC
6 | Tourism | Develoment and maintain tourism activities in 3 communities | 1.Ankaase 2.Amormorso3. Tebso I | New | Tourism site developed |  |  |  |  | 20000 |  | 500000 | Planning Unit and Tourism Authority | DA
Agriculture Development
7 |  | Completion of office block for District Agric. Directorate | Asiwa | On-going | Agric. Block completed |  |  |  |  | 200000 |  |  | AGRIC. DEPT. | DA
8 |  | Support Rice and mango Cultivation farms / Demonstration farms | Districtwide | New | Rice and mango cultivation /demonstration farms supported |  |  |  |  | 30000 |  | 5000 | AGRIC. DEPT./ DPO | DA
9 |  | Support 40 ruminant and poultry Farmers with Skills on effective construction of improved housing | Districtwide | New | Ruminant and poultry farmers supported |  |  |  |  | 6000 |  |  | AGRIC. DEPT. | DA
10 |  | Organise field tour to establish farms and reseach institute for 40 farmers | Bomfa Junction and Districtwide | New | Field tour to established farms organised |  |  |  |  | 20000 |  | 2000 | Agric. Dpt | DA
SUB-TOTAL
Adopted MDAs Goal(s): CREATE AN EQUITABLE, HEALTHY AND DISCIPLINE SOCIETY
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG/DACF | DDF | Donor/IGF | Lead | Collaborating
Social Services Delivery
11 | Health Delivery | Support the District Response Initiative (DRI) on HIV/AIDS and Prevention of Malaria & MSHARP | Districtwide | New | HIV/AID's and Malaria prevention activity done |  |  |  |  | 40000 |  |  | DPO | DA
12 |  | Spport Covid-19 activities | Districtwide | New | Covid-19 activities supported |  |  |  |  | 50000 |  | 100000 | DHD,NADMO, ENV'TAL | DA
13 |  | Completion and furnishing of 1-No. CHPs Compound | Duase | New | CHP s Compound constructed |  |  |  |  | 300000 |  |  | Health | DHD
14 |  | Construction of 1 No. health Facility | Danso | New | Health facility constructed |  |  |  |  | 150000 |  |  | DPO/WORKS/DHD | DA
15 |  | Procure Basic equipment for CHPS compound and Laboratories | District wide | New | Hospital equipment procured |  |  |  |  | 30000 |  |  | DPO/WORKS/HEALTH DEPT. | DA
16 |  | Mechanisation of 1No. Borehole for Freboye CHP Compound | Freboye | on-going | CHPs completed |  |  |  |  | 15000 |  |  | DPO/WORKS/HEALTH DEPT. | DA
17
18 | Education | Fencing of Bosome Freho Sec. Tech. Sch | Asiwa | Old | Fencing of SHS completed |  |  |  |  | 43885 |  |  | DPO/WORKS/EDUC. | DA
19 |  | Completion of 1No. 6-Unit Classroom Blk | Bobiam | on-going | 6-Unit Classroom block completed |  |  |  |  | 127352 |  |  | DPO/WORKS/EDUC. | DA
20 |  | Constraction of 1No. 3-Unit classroom Blk | Amantubuom | on-going | 3-Unit Classroom block completed |  |  |  |  | 150000 |  |  | DPO/WORKS/EDUC. | DA
21 |  | Construction of 1No. 6-unit classroom Blk | Nsueam II | on-going | 3-Unit Classroom block completed |  |  |  |  | 200000 |  |  | DPO/WORKS/EDUC. | DA
22 |  | Construction of 1No. 6-unit classroom Blk | Tebeso II | on-going | 3-Unit Classroom block completed |  |  |  |  | 150000 |  |  | DPO/WORKS/EDUC. | DA
23 |  | Completion of 1No. 3-Unit Classroom Blk | Ohwimase | on-going | 3-Unit Classroom block completed | [5 empty] | 29000 |  | DPO/WORKS/EDUC. | DA
24 |  | Support MP's projects and programmes | Districtwide | New | MP's projects and programmes supported |  |  |  |  | 300000 |  |  | WKS, PLAN. MP | DA
25 |  | Construction of 1 No. 3-Unit Classroom Block | Minnti | New | 3-Unit Classroom Block Constructed |  |  |  |  | 300000 |  |  | WKS/DPO | GES
26 |  | Completion and finishing of 1 No. 3-Unit Classroom Block | Dajanso | Old | 3-Unit Classroom Block Constructed | [5 empty] | 38000 |  | WKS/DPO | GES
27 |  | Renovation of 1 No. 6-Unit RCC Primary School | Anyinaase | New | 6-Unit Classroom block Renovated | [5 empty] | 200000 |  | WKS/DPO | GES
28 |  | Renovation of 1 No. 6-Unit Presby Primary School | Asiwa | New | 6-Unit Classroom block Renovated | [5 empty] | 200000 |  | WKS/DPO | GES
29 |  | Renovation of 1 No. 6-Unit DA Primary School | Abosamso | New | 6-Unit Classroom block Renovated | [5 empty] | 200000 |  | WKS/DPO | GES
30 |  | Completion of 1No. 3-Unit Classroom Blk | Amormoso | old | 3-Unit Classroom block constructed |  |  |  |  | 12533.91 |  |  | DPO/WORKS/EDUC. | DA
31 |  | Completion of 1No. 3-Unit Classroom Blk | Dajanso | on-going | Teaching and learning materials provided |  |  |  |  | 37065.58 |  |  | DPO/WORKS/EDUC. | DA
32 | Social Welfare and Community Development | Community care; Register and Monitor PWD and LEAP programme | Districtwide | New | Communal labour supported |  |  |  |  | 5000 |  |  | COMM. DVPT. | DA
33 |  | Construction of 1 No. Community Centre | Yapesa | New | Community centre constructed |  |  |  |  | 0 |  |  | Wks | SW&CD
34 |  | Support Child Right Promotion and Protection activities | Districtwide | New | Women and Children supported |  |  |  |  | 5000 |  |  | Social Welfare and Community Devt. | DA
35 |  | Support Justice Administration & Mass Education activities | Districtwide | New | Women and Children supported |  |  |  |  | 3635.41 |  |  | Social Welfare and Community Devt. | DA
SUB-TOTAL
Adopted MDAs Goal(s): SAFEGUARD THE NATURAL NEVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG/DACF | DDF | Donor/IGF | Lead | Collaborating
Infrastructure Delivery & Management
36 | Infrastructure Development | Preparation of sector layout/ planning scheme | Anyanso, Tebeso II, Dannso and Nsuaem II | New | Sector layout or planning scheme prepared |  |  |  |  | 60000 |  |  | DPP/WORKS/DPO | DA
37 |  | Undertake street naming and property addressing activity | Anyanso, Tebeso II, Anyinaase and Nsuaem IIAsiwa, Bobiam | New | Streets named and properties addressed |  |  |  |  | 50000 |  |  | DPP/WORKS/DPO | DA
38 |  | Maintenance of Quasi-Government Properties(Court Building, Assembly Block Streetlights, Police Station, Market, health facility etc) | District wide | on-going | Governmnent properties maintained |  |  |  |  | 15000 |  |  | DPO/WORKS | DA
39 |  | Construction and mechanisation of 1 No. borehole facility at the Senior Staff Quarters | Asiwa | New | Borehole constructed and mechanised |  |  |  |  | 30000 |  |  | Works /DPO | DA
40 |  | Drilling of 10 No. Boreholes | Selected communities | on-going | Boreholes drilled |  |  |  |  | 116795.5 |  |  | DPO/WORKS | DA
41 |  | Support Rural Electrification and Streetlights projects | district wide | on-going | Street lights /Rural electrification maintained |  |  |  |  | 50000 |  |  | DPO/WORKS | DA
42 |  | Construction of Culverts | Asiwa-Anumso road | New | Culverts constructed |  |  |  |  | 150000 |  |  | DPO/WORKS | DA
43 |  | Reshaping of 35KM Roads | District wide | on-going | Roads reshaped |  |  |  |  | 200000 |  |  | DPO/WORKS | DA
44 |  | Construction of bidge | Achiase-Annumso | New | Bidge constructed |  |  |  |  | 100000 |  | 50000 | WKS DPT. | DA
45 |  | Construction of 1-No. Semi-detached bungalow | Asiwa | on-going | Semi-detached bungalow constructed |  |  |  |  | 100000 |  |  | DPO/WORKS | DA
46 |  | Support / Undertake community initiated / Self Help Projects | District wide | on-going | Communities supported with materials |  |  |  |  | 250000 |  |  | DPO/WORKS | DA
47 |  | Monitor and Repair broken down boreholes / water system | Districtwide | New | Broken down boreholes monitored and repaired |  |  |  |  | 50000 |  |  | DPO/WKS/COM. DEVT. | DA
48 |  | Renovation of Assembly bungalows and quarters | Asiwa | New | Bungalows and quarters renovated |  |  |  |  | 100000 |  |  | EKS DPT. | DA
49 | Natural Resource Conservation | Dislodging of Septic Tank | District wide | New | Septic tank disloged |  |  |  |  | 15000 |  |  | Envital Health | DA
50 |  | Undertake fumigation activity | Districtwide | New | Fumigation done |  |  |  |  | 20000 |  |  | Envital Health | DA
51 |  | Planting of trees in disaster prone and open areas | District wide | New | Disaster prone areas mapped |  |  |  |  | 70000 |  |  | NADMO and Forestry | DA
52
53 |  | Re-afforestation of depleted forest and galamsey areas | Districtwide | New | Trees planted in depleted forest areas |  |  |  |  | 50000 |  |  | Forestry commission | DA
54 |  | Undertake food vendor screening activity | Asiwa | New | Food vendors screened |  |  |  |  | 50000 |  |  | Envital Health | DA
55 |  | Undertake disaster prevention Education Campaigns & supply of livelihood support items to disaster victims | District wide | New | Education campaign and relief items done |  |  |  |  | 30000 |  |  | NADMO | DA
| SUB-TOTAL | [12 empty] | DA
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG/DACF | DDF | Donor/IGF | Lead | Collaborating
Adopted MDAs Goal(s): BUILD EFFECTIVE, EFFICIENT AND DYNAMIC INSTITUTIONS
Management and Administration
56 | Finance and Revenue Mobilisation | Undertake Public Sensitization on Pay your Levy Campaign | District Wide | on-going | Public sensitise on revenue mobilisation |  |  |  |  | 10000 |  |  | FINANCE/BUDGET | DA
57
58 |  | Undertake revenue mobilisation activity in some selected communities | District Wide | on-going | Revenue mobilisation activities supported |  |  |  |  | 50000 |  |  | FINANCE/BUDGET | DA
59 | Human Resource Management
60 |  | Procure office equipment for staff | Asiwa | New | Office equipment procured |  |  |  |  | 15000 | 20000 |  | DPO/WKS | DA
61 |  | Undertake capacity building for Assembly members and staff of the Assembly | Asiwa | New | Assembly members and staff of the Assembly trained |  |  |  |  | 50000 |  |  | HR/DPO | DA
62 | Planning, Budgeting and Coordination | Undertake DPCU activities (2021-2025 MTDP Preparation) | Asiwa | on-going | DPCU activities supported |  |  |  |  | 70000 |  |  | DPO,BA | DA
63 |  | Support statistical activities (2021 census, market readings, database update and dissemination) | Districtwide | New | Statistical activities supported |  |  |  |  | 10000 |  |  | DS,DPO | DA
64 |  | Undertake Monitoring and Evaluation activity on projects and programmes | District Wide | on-going | Projects and programmes monitored aand evaluated |  |  |  |  | 40000 |  |  | DPO | DA
SUB TOTAL
| MDAProgrammes and Sub-programmes | Activities (Operations) | Location | Status | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies
[6 empty] | 1st | 2nd | 3rd | 4th | GoG/DACF | DDF | Donor/IGF | Lead | Collaborating
Adopted MDAs Goal(s):STRENGTHEN GHANA’S ROLE IN INTERNATIONAL AFFAIRS
Management and Administration
65 | General Administration, Legislative Oversight | Maintenance of Office machines/ euipment | Asiwa | on-going | Office machines maintained |  |  |  |  | 20000 |  |  | ADMIN. | DA
66 |  | Repair of official vehicles | Asiwa | New | Official Vehicles repaired |  |  |  |  | 70000 |  |  | ADMIN. | DA
67 |  | Strengthening of Sub-District structures | Area council centres | on-going | Area councils strengthened |  |  |  |  | 73927.83 |  |  | DPO | DA
68 |  | Renovation / Rehabilitation of Fire and Ambulance Stations | Asiwa | On-going | Fire and Ambulance station renovated |  |  |  |  | 100000 |  |  | Wks Dpt. | DA
69 |  | Support and Undertake security and emergency service activities | District Wide | on-going | Security agencies supported |  |  |  |  | 30000 |  |  | Police/Fire/Ambulance | DA
70 |  | Undertake public / town hall meetings | District Wide | New | Town Hall/ Public Forum organised |  |  |  |  | 50000 |  |  | DPO/BUDGET | DA
SUB TOTAL
GRAND TOTAL