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BOSOME FREHO 

     P.O. Box 365
 DISTRICT ASSEMBLY      Konongo-Ashanti
                                                                                        In case of reply the Number and 
                                                                                                    Date of letter should be quoted

                                                                                                    Our Ref:…………………………

         Your Ref:…………………………
         Date: 


2023 ANNUAL ACTION PLAN (AAP)
The Bosome Freho District Assembly exists to achieve the set goals and objectives under the 2022-2025 Medium Term Development Plan (MTDP).  
In view of this, attached is the Annual Plan for the year 2023 for Bosome Freho District Assembly for your perusal and action.
                                              for: DISTRICT CHIEF EXECUTVE
                                                           SAMUEL KYEI-BAFOUR FRIMPONG
                                           (DISTRICT COORDINATING DIRECTOR)
THE DIRECTOR GENERAL
NDPC

ACCRA-GHANA

THROUGH:

THE REGIONAL ECONOMIC PLANNING OFFICER

REGIONAL COORDINATING COUNCIL

KUMASI

BOSOME FREHO ANNUAL ACTION PLAN FOR THE YEAR 2023
	PBB Programme
	PBB Sub-programme
	Broad activities
	Time frame [Year e.g. 2023]
	Cost
	Implementing Institution/Department

	
	
	
	QTR1
	QTR2
	QTR3
	QTR4
	New
	On-going
	Lead
	Collaborating

	
	
	
	
	
	
	
	GOG (DACF)
	IGF
	DP (DDF, MAG)
	GOG
(DACF)
	IGF
	DP
(DDF,MAG)
	
	

	Economic Development
	STRONG AND RESILIENT ECONOMY
	Train 600 enterprises in the Nsuta and Asiwa zone in Financial Management and Reporting
	
	
	
	
	5,000.00
	
	
	
	
	
	BAC
	DA

	
	
	Train 150 women and 100 men (youth) in soapmaking, beading making and baking and confectionery districtwide
	
	
	
	
	5,000.00
	
	
	
	
	
	BAC
	DA

	
	
	Completion of Block B of 20 No. Market Stores at Asiwa
	
	
	
	
	
	
	578,102.00
	
	
	
	Works
	DA

	
	
	Completion of setional completion of Block B Building of 10 No. Market Stores at Asiwa
	
	
	
	
	
	
	467,589.94
	
	
	
	Works
	DA

	
	
	Construction of concrate pavement of the entrance of Asiwa lorry park with 2 no. rest sheds, 10=seater Toilet facility
	
	
	
	
	
	
	367,878.91
	
	
	
	works
	BA

	
	
	Sectional completion of Block A
	
	
	
	
	
	
	642,997.82
	
	
	
	works
	DA

	
	
	Completion of pavement of lorry park at Asiwa
	
	
	
	
	
	
	4,383.22
	
	
	
	Works
	DA

	
	
	Provide business counselling and advisory services to all enterprises district wide
	
	
	
	
	5,000.00
	
	
	
	
	
	BAC
	DA

	
	INDUSTRIAL TRANSFORMATION
	Support the facilitation and implementation of a 1D, 1F programme for 40 stakeholders at Asiwa/Anyanso
	
	
	
	
	50,000.00
	
	
	
	
	
	DAD
	DA, MoFA

	
	
	Support the Renovation of Bosome Freho Rural Bank Building at Nsuem II and the provision of concrate benches at Ankaase
	
	
	
	
	
	63,563.34
	
	
	
	
	works
	DA

	
	
	Facilitate access to modern startup kits for 60 artisans districtwide
	
	
	
	
	
	
	
	
	
	
	SW&CD, BAC, DAD
	DA, NBSSI

	
	PRIVATE SECTOR DEVELOPMENT
	Assist 250 women and 150 men artisans to gain register general certification                                            
	
	
	
	
	3,000.00
	
	
	
	
	
	BAC, DAD
	DA, Registrar General 

	
	
	Facilitate the granting of loan to 200 enterprises districtwide
	
	
	
	
	2,000
	
	
	
	
	
	BAC
	DA, NBSSI

	
	
	Facilitate the acquisition of NVTI Certificate for enterprises in the service sector (hairdressing & dressmaking)
	
	
	
	
	5,000.00
	
	
	
	
	
	BAC
	NBSSI, DA

	
	AGRICULTURE AND RURAL DEVELOPMENT
	Training of 200 small ruminant farmers on breed improvement, Disease and pest management in small ruminant
	
	
	
	
	10,000.00
	
	
	
	
	
	DAD
	DA, MoFA

	
	
	Establish Sixteen (16) Rice demonstrations using sustainable rice extension plan at Anyanso, Anyinase, Nsuaem 2, Nsuta, Anomawobi, Freso, Korkyikrom communities
	
	
	
	
	20,000.00
	
	
	
	
	
	DAD
	DA, MoFA, NGO’s

	
	
	Identify and build the capacity of 60 input dealers/other service providers to ensure compliance and better services to farmers in the district (MAG)
	

	
	
	
	10,000.00
	
	10,000.00
	
	
	
	DAD
	DA, MoFA, NGO’s

	
	
	Organize trainings on leguminous, sucker and vegetable crop farmers on post-harvest and climate smart agricultural technologies districtwide
	
	
	
	
	10,000.00
	
	50,000.00
	
	
	
	DAD
	DA, MoFA, NGO’s

	
	
	Establish Six (6) adaptive trial on the effective control of cabbage Diamondmoth back and blight at Adeito, brofoyedu, Kokobeng, Adakabunsu, Morontuo 
	
	
	
	
	10,000.00
	
	
	
	
	
	DAD
	DA, MoFA, NGOs

	
	
	Vaccination of 3000 small ruminants against  PPR, Newcastle, rabies (MAG) districtwide

	
	
	
	
	
	
	
	
	
	
	DAD
	DA, MoFA

	
	
	Completion of 1 No. Office Block for Agric. Directorate at Asiwa
	
	
	
	
	
	
	
	100,000.00
	
	
	Works
	DA, DAD

	
	
	Undertake food security activity districtwide
	
	
	
	
	15,000.00
	
	
	
	
	
	DAD
	DA, MoFA

	
	
	Support to cocoa spraying gangs districtwide
	
	
	
	
	20,000.00
	
	
	
	
	
	DAD
	DA

	
	
	Construction of mini-warehouse for cocoabod and agricultural directorate
	
	
	
	
	80,000.00
	
	
	
	
	
	Works
	DAD, Cocobod

	
	FISHERIES AND AQUACULTURE DEVELOPMENT
	Creation of small irrigation dams for cabbage farmers at Adeito
	
	
	
	
	30,000.00
	
	50,000.00
	
	
	
	DAD
	DA, NGO’s

	
	
	Undertake awareness creation/ education activity on the agric. Sector’s policy for 40 farmers
	
	
	
	
	8,000.00
	
	
	
	
	
	DAD
	DA

	
	TOURISM AND CREATIVE INDUSTRY DEVELOPMENT
	Undertake or support tourism activities at Ankaase, Duase and Amormorso
	
	
	
	
	10,000.00
	
	100,000.00
	
	
	
	DPCU
	DA, GTA, NGO’s

	Social Development
	EDUCATION AND TRAINING
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	Completion of No. 3-Unit Classroom Block at Minnti
	
	
	
	
	
	
	
	286,183.68
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 6-Unit Classroom Block with office and storeroom at Tebeso II
	
	
	
	
	
	
	
	298,033.23
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 3-Unit Classroom Block with storeroom, and KVIP toilet facilities at Amantoboum
	
	
	
	
	
	
	
	259,767.98
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 6-Unit Classroom Block with office, storeroom and KVIP toilet facilities at Nsuaem II
	
	
	
	
	
	
	
	459,971.16
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 3-Unit Classroom Block at Asiwa
	
	
	
	
	
	
	
	127,352.00
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 3-Unit Classsroom Block at Owhimase
	
	
	
	
	
	
	
	28524.69
	
	
	Works
	DED, DA

	
	
	Completion of 1 No. 3-Unit Classsroom Block at Amormorso
	
	
	
	
	
	
	
	12,533.91
	
	
	Works
	DED, DA

	
	HEALTH AND HEALTH SERVICES
	Undertake District Response Initiatives on HIV/AIDs and Malaria cases districtwide
	
	
	
	
	21,233.50
	
	
	
	
	
	DAC
	DA

	
	
	Support for the cutting of land for the construction of agender 111 district hospital at Asiwa
	
	
	
	
	
	
	
	150,000.00
	
	
	Works
	DHD, DA

	
	
	Completion of CHPs compound at Dannso
	
	
	
	
	
	
	
	100,000
	
	
	Works
	DHD, DA

	
	
	Support the procurement of equipment for CHPs compounds districtwide
	
	
	
	
	30,000.00
	
	
	
	
	
	DHD
	DA

	
	
	Completion of 1 No. CHPs compound at Duase
	
	
	
	
	
	
	
	100,000
	
	
	DHD
	DA

	
	
	Construction of 1 No. office Acomnodation for the NHIA
	
	
	
	
	156,912030
	
	
	
	
	
	works
	DA

	
	FOOD AND NUTRITION SECURITY (FNS)
	Undertake food vendor screening activities districtwide
	
	
	
	
	20,000.00
	
	
	
	
	
	
	

	
	REDUCING POVERTY AND INEQUALITY
	Undertake community care activity (Register and monitor Person’s with disability (PWDs)) districtwide 
	
	
	
	
	6,000.00
	
	
	
	
	
	SW&CD
	DA, DHD, NHIS, 

	
	WATER AND ENVIRONMENTAL SANITATION
	Undertake fumigation and sanitation improvement activities at selected communities
	
	
	
	
	300,000.00
	
	
	
	
	
	DEH
	Zoomlion, DA

	
	
	Mechanisation of 1 No. Borehole at Freboye CHPS compound
	
	
	
	
	
	
	12,000.00
	
	
	
	Works
	DA

	
	
	Drilling of 10 No. boreholes at selected communities
	
	
	
	
	116,795.50
	
	
	
	
	
	Works
	DA

	
	
	Drilling and mechanisation of 1 No. borehole at Snr. Staff Quarters
	
	
	
	
	30,000.00
	
	
	
	
	
	Works
	DA

	
	
	Undertake dislodging of septic tank activity at Asiwa
	
	
	
	
	15,000.00
	
	
	
	
	
	DEH
	DA

	
	
	Support saniation programmes (noise control, sensitition and public education) 
	
	
	
	
	30,000.00
	
	
	
	
	
	DEH
	DA

	
	
	Undertake tree planting activities along water bodies and degraded land areas at Duase, Ankaase, Yapesa and Adakabruso
	
	
	
	
	15,000.00
	
	
	
	
	
	Forestry
	NADMO, DA, NGOs

	
	CHILD PROTECTION AND DEVELOPMENT
	Undertake child protection and  child rights promotion programme (especially the orphans and the vulnerable children inclusive)
	
	
	
	
	6,000.00
	
	6,000.00
	
	
	
	SW&CD
	DA, MGCSP, DONORS

	
	
	Undertake monitoring of child protection activities districtwide 
	
	
	
	
	5,000.00
	
	5,000.00
	
	
	
	SW&CD
	DA, MGCSP, DONORS

	
	
	Undertake Case management on child protection activities districtwide
	
	
	
	
	5,000.00
	
	5,000.00
	
	
	
	SW&CD
	DA,MGCSP,DONORS

	
	SUPPORT FOR THE AGED
	Undertake support for the aged programme (Leap Empowerment Against Poverty (LEAP) ) districtwide
	
	
	
	
	170,000.00
	
	
	
	
	
	SW&CD
	DA, MGCSP, NGOS

	
	SOCIAL PROTECTION
	Undertake justice administration and mass education towards social protection activities districtwide
	
	
	
	
	8,800.00
	
	
	
	
	
	SW&CD
	DA, MGCSP, NGOS

	
	DISABILITY-INCLUSIVE DEVELOPMENT
	Support the Ghana Employment and Social Protection Programme (Productive Inclusion Activities)
	
	
	
	
	
	
	20,000.00
	
	
	
	SW&CD
	DA, MGCSP, DONORS

	
	
	Undertake community care: registering and monitoring of PWDs districtwide
	
	
	
	
	6,000.00
	
	
	
	
	
	SW&CD
	DA, MGCSP, DONORS

	Environment, Infrastructure and Human Settlements
	ENERGY AND PETROLEUM
	Undertake or support rural electrification / street lights programme districtwide
	
	
	
	
	50,000.00
	
	
	
	
	
	Works
	DA, ECG

	
	HUMAN SETTLEMENTS DEVELOPMENT AND HOUSING
	Completion of 1 No. Semi-detached bungalow at Asiwa
	
	
	
	
	
	
	
	100,000.00
	
	
	Works
	DA

	
	
	Construction of 1 No. police Post with a charge Office, an Armory store, CID office, Station officers office and a Mechanized Borehole with 3000Lt capacity overhead water tank
	
	
	
	
	726,270.00
	
	
	
	
	
	works
	DA

	
	
	Reshaping of 8km of feeder roads districtwide
	
	
	
	
	150,000.00
	
	
	
	
	
	Works
	Feeder roads, DA

	
	
	Support for the monitoring of feeder roads districtwide
	
	
	
	
	11,396.75
	
	
	
	
	
	Works
	Feeder roads, DA

	
	RURAL DEVELOPMENT MANAGEMENT
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	Support community self-help projects districtwide
	
	
	
	
	212,334.98
	
	
	
	
	
	Plg
	DA, NGOS, DONORS

	
	
	Undertake self-help projects and other social intervention activities by the MP 
	
	
	
	
	250,000.00
	
	
	
	
	
	Works
	DA, DONORS

	
	INFRASTRUCTURE MAINTENANCE
	Maintenance of quasi-government properties (court building, police station, market etc.)
	
	
	
	
	15,000.00
	
	
	
	
	
	Works
	DA

	
	
	Renovation of DCE’s bungalow at Asiwa
	
	
	
	
	50,000.00
	
	
	
	
	
	Works
	DA

	
	
	Renovation of Office Building at Asiwa
	
	
	
	
	30,000.00
	
	
	
	
	
	Works
	DA

	
	
	Renovation of old Assembly Block for National Ambulance and Fire Service Station at Asiwa
	
	
	
	
	
	
	
	100,000.00
	
	
	Works
	DA

	
	LAND ADMINISTRATION
	Undertake the preparation of sector layout and planning schemes for Nsuaem No. 2
	
	
	
	
	40,000.00
	
	
	
	
	
	PP
	DA

	
	
	Undertake street naming and property addressing system districtwide
	
	
	
	
	30,000.00
	
	
	
	
	
	PP
	DA

	Governance, Corruption and Public Accountability
	LOCAL GOVERNANCE AND DECENTRALISATION
	Undertake pay-your levy campaign programme districtwide
	
	
	
	
	10,000.00
	
	
	
	
	
	Fin.
	DA

	
	
	Support the gazetting of Assembly bye-laws and fee fixing
	
	
	
	
	10,000.00
	
	
	
	
	
	Cent. Adm
	DA

	
	
	Undertake the strengthening of Sub-Structures (Area coucils) districtwide
	
	
	
	
	84,934.00
	
	
	
	
	
	Cent. Adm
	DA

	Emergency Planning and Response (Including Covid-19 Recovery Plan)
	GEOLOGICAL THREATS
	Undertake education campaign on disaster prevention and the distribution of relief items to disaster victims districtwide
	
	
	
	
	30,000.00
	
	
	
	
	
	NADMO
	DA

	
	
	Undertake road safety campaign programmes for motor and vehicle users districtwide
	
	
	
	
	30,000.00
	
	
	
	
	
	Police
	DA

	
	COVID-19 RESPONSE
	Support the control and management of COVID-19 and other pandemics districtwide
	
	
	
	
	30,000.00
	
	
	
	
	
	DHD
	DEH, DA,

	
	
	Undertake / support COVID-19 and other sanititon activities districtwide
	
	
	
	
	7,120.24
	
	
	
	
	
	DEH
	DHD, DA

	Implementation, Coordination, Monitoring and Evaluation
	IMPLEMENTATION AND COORDINATION
	Undertake / support the Action Plan and Budget preparation, implementation and coordination at all levels
	
	
	
	
	30,000.00
	
	
	
	
	
	Budget
	DA

	
	MONITORING AND EVALUATION
	Undertake monitoring and evaluation activities on all Assembly’s projects and programmes districtwide
	
	
	
	
	45,000.00
	
	
	
	
	
	DPCU
	DA

	
	PRODUCTION AND UTILISATION OF STATISTICS
	Support the production and utilisation of statistics in the district
	
	
	
	
	10,000.00
	
	
	
	
	
	Statistics
	DA


